## Sprints Planning
# | Task | Responsible | start work day | End work day | Duration (day) | Status | Notes
Sprint 1
1 | Signup | Dev 1 | 1 | 6 | 5 | Done
2 | Login | Dev 2 | 2 | 6 | 4 | In progress
3 | User Settings | Dev 3 | 6 | 11 | 5 | Todo | address, favorites
4 | Restaurants listview | Dev 4 | 1 | 4 | 3 | Done | name, logo, delivery speed, rating
5 | Restaurant menu listview | Dev 1 | 2 | 5 | 3 | Done | item name, image, rating, quick description, add to cart
6 | Cart | Dev 4 | 6 | 12 | 6 | Todo | Cart summary, items, vat, variable delivery fees
7 | Restaurant Admin UI Part1 | Dev 2 | 7 | 12 | 5 | Todo | Manage restaurant menu items.
8 | Restaurant Admin UI Part2 | Dev 1 | 8 | 13 | 5 | Todo | Manage incoming orders.
9 | User order tracking UI | Dev 3 | 9 | 12 | 3 | Todo | Track order text status (no maps)
Sprint 2 (planned on a later meeting)
1 | Integrate Visa Payments | Dev 1, Dev 2 | 1 | 7 | 6 | Todo
2 | Integrate Vodafone Cash | Dev 1, Dev 2 | 8 | 12 | 4 | Todo
3 | Voucher System | Dev 3 | 1 | 7 | 6 | Todo
4 | Delivery Live Tracking | Dev 4 | 1 | 7 | 6 | Todo
5 | Restaurant Admin Payments | Dev 4 | 11 | 14 | 3 | Todo | allow admins to choose supported forms
Sprint Planning Meeting
Part 1 - Scope
Goal of sprint:
Identify important base backlog items to kickstart our project for the first sprint.
Ready backlog items contributing to current sprint goal:
- Signup / Login / User settings
- Restaurants list
- Restaurant menu list
- User Cart
- Restaurant Staff/Admin Panel / UI
- User order tracking UI
- Rating system
Team Availability:
- All 4 team members.
Team Capacity:
- Reviewing team capacity rating feature will be postponed.
Items to include on the sprint backlog based on availabilty of team:
- All except rating system will be postponed to next sprint.
Team is confident that we will finish the required tasks on time.
Part 2 - Plan:
planned and identified tasks for each team member in the upcoming table.