## stakeholder-register
Mobile Discounts App
Risk Management
Risk | Description | Imapct | Probability | Strategy | How
Technical Risks | This includes issues with the technology or software used to develop the application, such as compatibility with different devices or operating systems, data security, or functionality problems. | High | Medium | Migtigate | Have a thorough testing phase to identify any technical issues, work with experienced developers and cybersecurity professionals, and plan for regular updates and maintenance.
Maps provider | Google maps goes down or malfunction | Medium | Low | Avoid | Plan for a quick substitute maps service provider that can be remotely reconfigured.
Competitors | With existing competitors in the market, it's possible that our application may not be well-received or may not gain traction. | Medium | High | Migtigate | Conduct a thorough market analysis to identify what sets your product apart, and plan marketing and promotion strategies to differentiate it from competitors.
Financial Risks | This includes potential budget overruns, cost overruns, or unexpected expenses. | High | Medium | Migtigate | Develop a detailed budget and track expenses closely throughout the project, identifying any potential cost overruns early and making necessary adjustments.
Resources | This includes the availability and quality of resources, such as team members, equipment, or software. | Medium | Medium | Migtigate | Plan for contingency resources and identify potential risks to availability of resources, such as changes in personnel, equipment failure, or vendor delivery delays.
User Adoption | It's possible that users may not find the application user-friendly, or may not adopt it as expected. | Medium | High | Escalate | Escalate to R&D, conduct user testing and surveys throughout development to identify any user adoption issues, and make necessary adjustments based on feedback. Plan for user education and training to increase adoption and usage.